## Sheet1
Sprint 4 Backlog
Task | Priority | Assignee | Estimated Hours | Taken Hours
Create boards, stages, taskItem model | 1 | Nick | 1 | 1
Create/delete tasks | 1 | Nick | 3 | 3
Database implementation of boards, stages, and tasks | 1 | Nick | 2 | 2
Create boards controller | 1 | Nick | 2 | 2
Boards controller testing | 1 | Nick | 2 | 2
ERD Diagram | 1 | Nick | 1 | 1
Updating user stories and use case diagram | 1 | Nick | 1 | 1
Move tasks | 1 | Nate | 2 | 2
Assign tasks | 1 | Nate | 3 | 3
Boards page navigation bug fixes | 1 | Nate | 1 | 1
Class diagram | 1 | Nate | 2 | 2
|  |  | Total | 20