## Sheet1
Sprint 3 Backlog
Task | Priority | Assignee | Estimated Hours | Taken Hours
Make Boards Page | 2 | Nick | 4 | 0
Employee - Project lead deletion check | 1 | Nate | 2 | 1
Stop bypass of login | 1 | Nick | 2 | 1
Displaying Manager/Lead name for group/project pages | 2 | Nate | 1 | 1
Fix bug: cannot log in after logging out | 1 | Nick | 2 | 1
Testing for employee page | 1 | Nick | 2 | 4
Testing for group page | 1 | Nick | 2 | 2
Testing for project page | 1 | Nate | 2 | 2
Testing for boards page | 2 | Nick | 2 | 0
Add dropdown to admin/standard employee create | 1 | Nick | 1 | 1
Group editing validation for admins and managers. | 1 | Nate | 2 | 2
Project editing validtion for admins and leads. | 1 | Nate | 2 | 2
Group creation validation for admins. | 1 | Nate | 2 | 2
Project creation validtion for admins and managers. | 1 | Nate | 2 | 2
|  |  | Total | 21