## Sheet1
As a… | I want to … | so that… | Time Alotted | Person Assigned
All | Be able to login/logout (web) | I can use the system | 4
Admin | Add/Delete Employees (web) | I can control who is in the system | 4
Admin | Create Groups (web) | I can organize employees into collaborative groups with a manager supervising work for the group | 8
Manager | Create Projects (web) | I can assign work to groups | 4
Manager | Assign a group to a project (web) | I can control who is actively collaborating to complete a project | 8
Manager | Edit the title and description of a project (web) | I can assign a name and description for the project to help others understand the purpose of the project | 2