## Sheet1
Task | Priority | Assignee | Hours
Make Boards Page | 2 | Nick | 4
Employee - Project lead deletion check | 1 | Nate | 2
Stop bypass of login | 1 | Nick | 2
Displaying Manager/Lead name for group/project pages | 2 | Nate | 1
Only Admin and Manager can edit Groups | 1 | Nate | 1
Fix bug: cannot log in after logging out | 1 | Nick | 2
Testing for employee page | 1 | Nick | 2
Testing for group page | 1 | Nate | 2
Testing for project page | 1 | Nate | 2
Testing for boards page | 2 | Nick | 2
Add dropdown to admin/standard employee create | 1 | Nick | 1