## Sheet1
Priority | As a… | I want to be able to… | So that… | Assigned To | Estimated Hrs | Week 1 Hrs | Week 2 Hrs | Total Hrs
1 | Admin | View, Create, and Delete Employee | I can manage the set of employees in the system | Nick | 6 | 4 | 4 | 8
1 | Admin | Promote/Demote Employee to/from Manager for a Group | I can manage who is supervising a particular group of employees | Nate | 2 | 0 | 2 | 2
1 | Admin | View, Create, and Delete Groups | I can organize employees into collaborative groups with a manager supervising work for the group | Nate | 4 | 0 | 4 | 4
1 | Manager* | View, Create, and Delete Projects | I can assign work to groups | Nate | 4 | 0 | 3 | 3
1 | Manager* | Assign/Remove Group to/from Project | I can control who is actively collaborating to complete a project | Nick | 3 | 0 | 0 | 0
1 | Manager* | Edit Title and/or Description of Project | I can assign a name and description for the project to help others understand the purpose of the project | Nick | 2 | 0 | 2 | 2